## Self-Publishing Checklist
BOOK TITLE
| TARGET PUBLICATION DATE | 2017-10-01 |  | <———— Enter date [ex: 10/1/17] or leave empty to customize your own deadlines
✓ | Task | Deadline | Suggested deadline | Typical time for completion
| If hiring a publicist, research and retain | 2017-01-01 | 9 months prior to pub date | 2-4 weeks
| Review 15-Tab Book Marketing Spreadsheet, add list items here for your campaign [http://bit.ly/Tbookmarketing] | 1/117 | 9 months prior to pub date | 1-2 days
| If needed, establish author social media accounts | 2017-01-01 | 9 months prior to pub date | 1 day
| Update social media profiles with upcoming title |  | as soon as title or cover ready | 1 day
| Send advance copies out for trade review | 2017-06-01 | 4 months prior to pub date | several days
| Send advance copies out for blurbs | 2017-06-01 | 4 months prior to pub date | several days
| Hire author website developer/designer, if needed | 2017-06-01 | 4 months prior to pub date | 1-2 months
| Establish formal email newsletter list, if needed | 2017-07-01 | 3 months prior to pub date | 1 week
| Make yourself complete the author questionnaire | 2017-07-01 | 3 months prior to pub date | 1 week
| Based on questionnaire, list who might publicize or review | 2017-07-01 | 3 months prior to pub date | 1 week
| Brainstorm pitches and angles for book publicity | 2017-07-01 | 3 months prior to pub date | 1 week
| If having a book launch event, set date and venue | 2017-07-01 | 3 months prior to pub date | 2 weeks
| Draft email templates for pitching media and others | 2017-08-01 | 2 months prior to pub date | 1 week
| Send pitches for publicity/reviews and follow-up as needed | 2017-08-01 | 2 months prior to pub date | ongoing
| Draft emails about your book to send to friends on pub day | 2017-09-01 | 1 month prior to pub date | 1 week
| Send invites for book launch party | 2017-09-01 | 1 month prior to pub date | 1 day
| Add endorsements/reviews to your retail book description |  | as they come in | 1 day
| Post on social media accounts with link to buy | 2017-10-01 | on pub date | 1-2 weeks
| Personally email all close friends/colleagues about release | 2017-10-01 | on pub date | 1 day
| Update your author website with links to buy | 2017-10-01 | on pub date | 1 day
| Update your author bios online with new release info | 2017-10-01 | by pub date | 1 day
| Check your Amazon Author Central page for accuracy |  | after pub date | 1 day
| Check your Goodreads author profile for accuracy |  | after pub date | 1 day