## Self-Publishing Checklist
BOOK TITLE
| TARGET PUBLICATION DATE |  |  | <———— Enter date [ex: 9/1/18] or leave empty to customize your own deadlines
✓ | Task | Deadline | Suggested deadline | Typical time for completion
| Research and finalize the title and subtitle |  | as early as possible
| Write book description and back cover copy |  | as early as possible
| Research/write a creative brief on cover design |  | as early as possible
| Send final manuscript to copyedit |  | 3 months prior to pub date | 2-4 weeks
| Hire out the cover design (send creative brief) |  | 3 months prior to pub date | 2-4 weeks
| Review the copyedit and resolve all issues |  | 2 months prior to pub date | 1-2 weeks
| Finalize the front cover design |  | 2 months prior to pub date
| (For print) Send final ms to interior design |  | 2 months prior to pub date | 2-4 weeks
| Write author bio, dedication, acknowledgments |  | 2 months prior to pub date
| (For print) Review designed pages; adjust/revise |  | 1 month prior to pub date | 1-2 weeks
| (For print) Complete back cover design + spine |  | 1 month prior to pub date | 1-2 weeks
| (For print nonfiction) Send final files to indexer |  | 3-4 weeks prior to pub date | 1-2 weeks
| (For digital) Create EPUB/MOBI files |  | 2-4 weeks prior to pub date | varies by process used
| Proofread final files in all formats |  | 1-2 weeks prior to pub date | 1-2 weeks
| Purchase ISBNs (myidentifiers.com), if using |  | any time
| Research/determine price point for all formats |  | any time; can be changed
| Research/determine BISAC codes or categories |  | any time; can be changed
| Research/determine keywords |  | any time; can be changed
| Upload print book files to CreateSpace |  | 1 week prior to pub date
| Review digital page proofs at CreateSpace |  | 5-7 days prior to pub date
| Order print (POD) copy from CreateSpace |  | 5-7 days prior to pub date
| Put book on-sale after reviewing print copy |  | around pub date
| Repeat process at IngramSpark, if using |  | when ready
| Upload ebook files to Amazon KDP |  | on pub date or 24h prior
| Upload ebook files to other retailers, as desired |  | on pub date or 24h prior